## Sheet1
ACTUAL WORK AT LG7 BY KASIDECH SITE EN.
No | Description | 2007-01-01 | [30 empty] | 2007-02-01 | [27 empty] | 2007-03-01
|  | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Span |  | 2007-01-01 TUE 23: RPN954-955(36m); 2007-02-01 SUN 4: RPN955-956(36m); 2007-02-01 TUE 13: RPN956-957(32m); 2007-02-01 TUE 20: RPN957-958(32m); 2007-02-01 SAT 24: RPN958-959(36m); 2007-02-01 WED 28: RPN959-960(36m); 2007-03-01 SUN 4: RPN960-961(32m); 2007-03-01 WED 7: RPN961-962 (32 m.)
1 | Lifting and Hanging Segments | 2007-01-01 FRI 5: H o l I d a y; 2007-01-01 FRI 12: H o l I d a y; 2007-01-01 FRI 19: H o l I d a y; 2007-01-01 FRI 26: H o l I d a y; 2007-02-01 FRI 2: H o l I d a y; 2007-02-01 MON 5: 2nos; 2007-02-01 TUE 6: 3nos; 2007-02-01 WED 7: 5nos; 2007-02-01 FRI 9: H o l I d a y; 2007-02-01 FRI 16: H o l I d a y; 2007-02-01 TUE 20: 6hrs; 2007-02-01 FRI 23: H o l I d a y; 2007-03-01 FRI 2: H o l I d a y; 2007-03-01 FRI 9: H o l I d a y; 2007-03-01 SAT 10: 4.5hrs; 2007-03-01 FRI 16: H o l I d a y; 2007-03-01 FRI 23: H o l I d a y; 2007-03-01 FRI 30: H o l I d a y
segments no come | bar: 2007-03-01 WED 7 to 2007-03-01 THU 8
| - Segments come | 2007-02-01 SUN 4: 5nos; 2007-02-01 TUE 6: 5nos; 2007-02-01 TUE 13: 5nos; 2007-02-01 WED 14: 4nos; 2007-02-01 TUE 20: 9nos; 2007-02-01 SAT 24: 6nos; 2007-02-01 SUN 25: 4nos; 2007-03-01 SUN 4: 9nos
2 | Gluing and Temp.PT work | 2007-02-01 WED 7: 7nos; 2007-02-01 THU 8: 3nos; 2007-02-01 TUE 20: 7hrs; 2007-02-01 SUN 25: 8hrs; 2007-03-01 SUN 11: 5.5 hrs
-Epoxy come
- Gloves come
- O-Ring come
Gluing and Temp.PT Record Sheet Signed and sent back | bar: 2007-03-01 SUN 4 to 2007-03-01 MON 5; 2007-03-01 SUN 11 to 2007-03-01 MON 12
3 | Threading of Strands and installation of Blocks and Wedges | 2007-02-01 WED 21: 5hrs; 2007-02-01 MON 26: 4hrs
| - Coils come | 2007-02-01 WED 7: 4nos; 2007-02-01 MON 12: 2nos; 2007-02-01 TUE 13: 3nos; 2007-03-01 SUN 4: 5nos
| - Blocks come | 2007-02-01 WED 28: 48no
| - Wedges come | 2007-02-01 WED 28: 4tim
- Plastic Noses come | bar: 2007-02-01 WED 28
When I got Treading of Strands Record Sheet | bar: 2007-03-01 SUN 4; 2007-03-01 WED 7
Treading of Strands Record Sheet Signed and sent | bar: 2007-03-01 TUE 6
4 | Stressing and Load Transfer work | 2007-02-01 SAT 10: 3hrs; 2007-02-01 SUN 11: 2hrs; 2007-02-01 WED 21: 3.5hrs; 2007-02-01 MON 26: 4hrs
When I got Tensioning Record Sheet from VFR | bar: 2007-03-01 SUN 4; 2007-03-01 WED 7
Tensioning Record Sheet signed and sent back | bar: 2007-03-01 TUE 6
When I got Load Transfer Sheet | bar: 2007-03-01 WED 7
Load Transfer Sheet Signed and sent back
5 | Remove Lifting Beam and Temp.PT Bracket | 2007-02-01 SUN 18: 2.5hrs; 2007-02-01 WED 21: 2hrs; 2007-02-01 THU 22: 1.5hrs
6 | Launching Gantry to Next Span | 2007-02-01 SUN 11: 5hrs; 2007-02-01 THU 22: 8.5hrs
When I got Launching Kinematics from VFR | bar: 2007-03-01 TUE 6
Launching Kinematics Signed and Sent back | bar: 2007-03-01 WED 7
7 | Permanent Bearing Installation and Span Adjustment | bar: 2007-03-01 WED 7 to 2007-03-01 THU 8; 2007-03-01 SAT 10
When I got Permanent Bearing Installation Record Sheet | bar: 2007-03-01 TUE 6
Permanent Bearing Installation Record Sheet Signd and sent back
8 | House Keeping | bar: 2007-03-01 WED 7 to 2007-03-01 THU 8; 2007-03-01 SAT 10
9 | Problems/Remarks | bar: 2007-03-01 WED 7 to 2007-03-01 THU 8; 2007-03-01 SAT 10 to 2007-03-01 SUN 11
Note on AK10: 10,1,9,8,7
Note on AL8: 10,1
Note on AM8: 9,8,7
Note on AM10: 2,3,4,5,6
Note on AN8: 2,3,4,5,6
Note on AN12: 1,2,3,4,5,6,7
Note on AO12: 8,9,10
Note on AQ24: on morning the Engineer stop work because of the document they requested but no response from VFR S01,C01,S02,S07,S08
Note on AR24: 07:00-09:00 stressing work S09,C10,S12,C02,C03,C04
Note on AR29: from 09:00
Note on AR30: 15:00-20:00 problem about RS relocation from megoshor beam
Note on AS18: for span RPN956-957
Note on AT10: 1,6,7,8,9 segment no.8 position of holes have not in positioned
Note on AT18: for Next Span too
Note on AU10: 2,3,4,5
Note on AV24: can stressing only 40%S01 and cannot continue because span have not in position and hardly to transfer load to jacks and must adjust span first
Note on AX24: cannot continue stressing and must adjust span first (use big jacks)
Note on AY24: continue stressing work and load transfer completely
Note on AY29: 16:00-18:30
Note on BA10: 1-9
Note on BA12: 13:30-20:30
Note on BB17: 0730-1230
Note on BB24: 13:00-16:20
Note on BC30: 07:00-16:30
Note on BE10: 10,9,8,7,6,1
Note on BF10: 2,3,4,5
Note on BF12: 11:00-19:00
Note on BG17: 07:30-11:30
Note on BG24: 13:30-1730
Note on BO35: from Dildo but Mr.Jay-QC Durl have comment and I will talk to Dildo
Note on BP9: no Temp.Bracket
Note on BP22: RPN961-962 from Julian
Note on BP25: RPN961-962 from Julian
Note on BP27: RPN961-962 from Julian
Note on BP32: RPN960-961
Note on BP34: RPN954-955, RPN955-956, RPN956-957
Note on BP37: House Keeping and Preparation work
Note on BP38: go to LG4 for help Ton something about Stressing sheet but have problem it's VSL trumplate but Freyssinet Block..Solution is change blocks to VSL then tomorrow can start stressing at LG4
Note on BQ9: no Temp.Bracket
Note on BQ34: RPN957-958
Note on BQ37: clean office.store and area of work (office at RPN961)
Note on BQ38: Clear Permanent Record Sheet with Dildo tell hime about not in positined of segments but adjusted follow by surveyor already and ask him to talk with Jay-Durl for conclusion
Note on BS8: 07:30-12:00
Note on BS10: all segments 9,8,7,6,1,2,3,4,5
Note on BS34: ,RPN958-959 ,RPN959-960
Note on BS38: can not start gluing work because of Temp.PT bracket don't come to site (will come from LG6) working time=07:00-18:00
Note on BT12: Temp.PT Bracket and Bars on site at 09:30 and start gluing at 11:30 finish at 18:00
Note on BT16: signed by Jay-QC JTM 18:20
Note on BT38: Temp.PT Bracket come 09:30
Note on BU16: sent back to Julian Table at 07:00